PROJECT REPORT

Task Dependency Visualizer

Topological Sort and Depth-First Search for Project Scheduling

Problem 93 | Design and Analysis of Algorithms

Submitted by

[Trisha Venkatraman Yelpula]

[25MVCSMR0706]

]

[CSE AI ML]

[MALLA REDDY VISHWAVIDYAPEET(TECHNICAL CAMPUS)]

3RD October 2026

1. Abstract and Introduction

1.1 Abstract

Projects are made of tasks, and many tasks cannot begin until others are finished. If these dependencies form a loop, no valid schedule exists. This report presents the Task Dependency Visualizer, a browser-based prototype that accepts a list of tasks with their dependencies, represents them as a directed graph, and produces either a valid execution order or a clear explanation of why none exists. The prototype implements two classic algorithms: Kahn's topological sort and a depth-first-search (DFS) based topological sort with cycle detection. Both run in O(V+E) time. Every step of each algorithm is recorded and can be replayed on an interactive graph, so the user sees the decisions being made and not only the final answer. For schedules without cycles, the tool also computes earliest start and finish times and the critical path.

1.2 Introduction

Scheduling work with prerequisites is a common real-world requirement in software projects, construction, course planning and build systems. The underlying model is a directed graph in which each task is a vertex and each dependency is an edge pointing from the prerequisite to the dependent task. A valid schedule is a topological ordering of this graph, and such an ordering exists if and only if the graph is a directed acyclic graph (DAG).

The prototype turns this theory into a tool that a project manager or student can use directly. It highlights which task is being processed, what has been unlocked, and, when a cycle exists, exactly which tasks form it.

2. Problem Statement, Objectives and Scope

2.1 Problem Statement

Visualize project task dependencies and detect cycles that make a schedule impossible.

2.2 Objectives

- Represent task dependencies as a directed graph using an adjacency list.

- Produce a topological order that respects every dependency, using two different algorithms (Kahn and DFS).

- Detect cycles and report them clearly, including the exact cycle path where possible.

- Make the algorithm's decisions visible through step-by-step animation of the graph.

- Compare the behavior of the two algorithms and present the final result in a form users can understand.

2.3 Scope

In scope: entering tasks with optional durations and dependencies as text; running both algorithms; step-through visualization; cycle reporting; critical path and earliest start/finish times for acyclic input; an on-page comparison table.

Out of scope: resource constraints, task assignment to people, calendar dates and holidays, saving projects on a server, and very large graphs (the layout is designed for graphs of roughly 5 to 20 tasks).

3. Features and Functional Requirements

3.1 Features

- Text-based task entry in the form Name(days): dependency, dependency.

- Two built-in examples: a valid website-launch plan and a plan that contains a cycle.

- Algorithm selector to switch between Kahn's algorithm and DFS.

- Step controls: Step, Back, Play/Pause and Reset, with a one-line explanation for each step.

- Colored graph: unvisited, in queue / in progress, done, and cycle / blocked states.

- Results panel: both topological orders, the cycle path or blocked tasks, and the critical path with total duration.

- Comparison table of strategy, cycle signal, cycle output, complexity and step count.

3.2 Functional Requirements

| ID | Requirement |
| --- | --- |
| FR1 | The system shall accept a list of tasks, optional durations and dependencies. |
| FR2 | The system shall create tasks mentioned only as dependencies automatically. |
| FR3 | The system shall build a directed graph with an edge from each prerequisite to its dependent task. |
| FR4 | The system shall compute a topological order with Kahn's algorithm. |
| FR5 | The system shall compute a topological order with DFS finish times. |
| FR6 | The system shall detect a cycle and state that no complete order is possible. |
| FR7 | The system shall display the cycle path found by DFS and the blocked tasks found by Kahn. |
| FR8 | The system shall let the user step through, replay and reset each algorithm. |
| FR9 | For an acyclic graph, the system shall compute earliest start, finish, project length and critical path. |

Non-functional requirements: runs in a modern browser with no installation or server; responds instantly for small graphs; works in light and dark themes; usable on desktop and mobile screens.

4. Algorithms and Methodology

4.1 Data Representation

Each task is stored with its name, duration and dependency list. From these, an adjacency list adj[u] is built, containing every task that depends on u, together with an edge list used for drawing. The adjacency list needs O(V+E) space and lets an algorithm visit all neighbors of a task in time proportional to their number.

4.2 Kahn's Algorithm (Indegree Queue)

The indegree of a task is its number of unfinished dependencies. Tasks with indegree 0 are ready and are placed in a queue. Removing a ready task adds it to the order and reduces the indegree of its dependents; any dependent that reaches 0 becomes ready.

compute indegree[v] for every task v

queue = all tasks with indegree 0

while queue is not empty:

u = dequeue(); append u to order

for each v in adj[u]:

indegree[v] -= 1

if indegree[v] == 0: enqueue(v)

if length(order) < V: cycle exists

Cycle detection: if the queue empties before every task is placed, the remaining tasks each wait for another remaining task, so a cycle exists. Kahn's algorithm reports this blocked set, which includes tasks on the cycle and tasks that depend on it.

4.3 DFS-Based Topological Sort

DFS explores as deep as possible along dependency edges. Each task has one of three states: unvisited, in progress (on the recursion stack) or finished. A task is appended to the finish list only after every task that depends on it has finished, so reversing the finish list gives a valid topological order.

visit(u):

state[u] = IN_PROGRESS; push u on stack

for each v in adj[u]:

if state[v] == UNVISITED: visit(v)

else if state[v] == IN_PROGRESS: cycle = stack from v to u, then v

pop stack; state[u] = FINISHED; append u to finish list

order = reverse(finish list)

Cycle detection: an edge to an in-progress task is a back edge, and a directed graph has a cycle if and only if DFS finds a back edge. The slice of the stack from that task to the current task, closed with the task itself, is the cycle.

4.4 Critical Path

For an acyclic graph, tasks are processed in topological order. The earliest start of a task is the largest finish time among its dependencies (0 if it has none), and its finish time is the start plus its duration. The task with the largest finish time marks the project length, and tracing back through the dependencies that determined each start time gives the critical path. A delay in any task on this path delays the whole project.

4.5 Visualization Methodology

Each algorithm records a snapshot after every step, containing the color of every task and a plain-language explanation. The interface does not recompute anything when the user presses Step or Back; it displays the stored snapshot. Acyclic graphs are drawn in columns by longest-path depth, so edges flow left to right. Graphs with a cycle are drawn on a circle so the loop is easy to see.

4.6 Complexity

|  | Kahn | DFS |
| --- | --- | --- |
| Time | O(V+E) | O(V+E) |
| Space | O(V) | O(V) including recursion stack |
| Cycle information | Set of blocked tasks | Exact cycle path |
| Critical path | O(V+E) after ordering | O(V+E) after ordering |

5. Technologies and Implementation

5.1 Technologies

| Technology | Purpose |
| --- | --- |
| HTML | Page structure, text area for task input, controls |
| CSS | Layout, light and dark themes, responsive design |
| JavaScript (vanilla) | Parsing, graph construction, both algorithms, critical path, step replay |
| SVG | Drawing nodes, arrows, colors and labels |

The whole prototype is one self-contained HTML file with no external libraries, so it runs offline in any modern browser.

5.2 Code Structure

| Function | Role |
| --- | --- |
| parse(text) | Reads lines, creates tasks, builds adjacency list and edge list |
| kahn(g) | Runs Kahn's algorithm and records a snapshot per step |
| dfs(g) | Runs DFS, records snapshots, finds finish order and the first cycle |
| crit(g, order) | Computes start/finish times, project length and critical path |
| layout(g, acyclic, order) | Chooses node positions (columns or circle) |
| draw() | Renders the current snapshot as SVG and updates the log |
| run() | Connects everything: parse, run both algorithms, fill the results and comparison |

5.3 Implementation Notes

- Tasks that appear only as dependencies are created automatically with a default duration of 1.

- Duplicate dependencies on a task are ignored.

- DFS continues after the first cycle so all tasks are visited, but only the first cycle is reported.

- The comparison table reports step counts taken from the recorded snapshots.

6. Results, Testing and Performance

6.1 Test Cases

The cases below were traced by hand from the algorithm definitions and match the two built-in examples. Running them in the prototype is the way to confirm them.

| # | Input | Expected result |
| --- | --- | --- |
| 1 | Website launch: Design(3); Content(4): Design; Backend(5): Design; Frontend(6): Design, Content; Integration(2): Backend, Frontend; Testing(3): Integration; Launch(1): Testing | Valid. Kahn: Design, Content, Backend, Frontend, Integration, Testing, Launch. DFS: Design, Backend, Content, Frontend, Integration, Testing, Launch. Project length 19 days. |
| 2 | Cycle plan: Plan(2); Build(4): Plan, Review; Test(3): Build; Review(2): Test; Ship(1): Review | No schedule. DFS cycle: Build, Test, Review, Build. Kahn releases only Plan; Build, Test, Review and Ship stay blocked. |
| 3 | Single task: A | Valid. Order: A. |
| 4 | Two independent tasks: A; B | Valid. Both are ready at the start; any order is correct. |
| 5 | Self-dependency: A: A | Cycle detected (A depends on itself). |
| 6 | Unknown dependency: B: A (A never defined) | A is created automatically; order A, B. |
| 7 | Empty input | Message asking for at least one task. |

6.2 Result for Test Case 1

Both algorithms return valid but different orders, which is expected because a DAG usually has many topological orders. Earliest start and finish days are: Design 0-3, Content 3-7, Backend 3-8, Frontend 7-13, Integration 13-15, Testing 15-18, Launch 18-19. The critical path is Design, Content, Frontend, Integration, Testing, Launch, with a total of 19 days. Backend is not critical: it finishes on day 8, while Integration cannot start until Frontend finishes on day 13.

6.3 Result for Test Case 2

Both algorithms agree that no schedule is possible. DFS names the cycle Build, Test, Review, Build: Build needs Review, Review needs Test, and Test needs Build. Kahn also stops early and leaves four tasks blocked. Ship is blocked only because it depends on Review, which shows the difference between the two outputs: Kahn reports everything affected, while DFS pinpoints the loop itself.

6.4 Algorithm Comparison

| Aspect | Kahn | DFS |
| --- | --- | --- |
| Strategy | Repeatedly remove tasks with no unmet dependencies | Go deep, record finish order, reverse it |
| Cycle signal | Some tasks never reach indegree 0 | Edge to a task that is still in progress |
| Cycle output | Blocked set only | Exact cycle path |
| Snapshots, test 1 | 8 steps | 14 steps |
| Natural fit | Showing which tasks can run in parallel | Reachability and structural analysis |

6.5 Performance

Both algorithms visit each task once and examine each dependency once, so running time grows linearly with V+E. For the graph sizes this prototype targets, computation is effectively instantaneous and the visible time is spent on drawing. Formal timing benchmarks on large graphs were not part of this prototype; for large inputs the SVG rendering and the layout, not the algorithms, would become the limit.

7. Conclusion, Future Scope and References

7.1 Conclusion

The Task Dependency Visualizer shows that a scheduling problem with prerequisites can be solved, explained and visualized with two simple linear-time graph algorithms. Kahn's algorithm makes the idea of "ready tasks" easy to see, while DFS gives the precise cycle that blocks a schedule. Recording every step turns the algorithms from a black box into something a user can follow, and the critical path adds practical value for planning. The prototype meets its objectives of producing a valid order, detecting cycles, and presenting the result clearly.

7.2 Limitations

- Input is text only; the graph cannot be edited by dragging.

- Only the first cycle is reported by DFS; other cycles in the same graph are not listed.

- The layout is suited to small graphs and does not minimize edge crossings.

7.3 Future Scope

- Interactive graph editing (add, move and delete tasks and edges on the canvas).

- Listing all cycles, or the strongly connected components, using Tarjan's or Kosaraju's algorithm.

- Suggesting which dependency to remove to break a cycle.

- Resource-constrained scheduling and assignment of tasks to people.

- Calendar dates, import and export (CSV, JSON), and saving projects.

- Better layout for large graphs and performance benchmarks.

7.4 References

- T. H. Cormen, C. E. Leiserson, R. L. Rivest and C. Stein, Introduction to Algorithms, 3rd ed., MIT Press, 2009 (chapter on elementary graph algorithms: DFS and topological sort).

- A. B. Kahn, "Topological sorting of large networks," Communications of the ACM, vol. 5, no. 11, pp. 558-562, 1962.

- R. Sedgewick and K. Wayne, Algorithms, 4th ed., Addison-Wesley, 2011 (directed graphs and topological sort).

- J. E. Kelley Jr. and M. R. Walker, "Critical-path planning and scheduling," Proceedings of the Eastern Joint Computer Conference, 1959.